Research team: Minutes for 11/15/23 Zoom meeting (7-8 pm EST)

https://wellforce-hipaa.zoom.us/j/5788493823?from=addon

Present: Josephine Harrington, Maryjane Farr, Natalie Tapaskar, Nadia Fida, Varinder Randhawa, Andriana Nikolova, Amanda Vest

- SGLT2i cohort study (Joey and Priya): Instructions, a version of the protocol, the REDCaps data capture tool and the template DUA are all available here:

https://www.dropbox.com/scl/fo/5aoxp6w7vousfx9g0ruw2/h?dl=0&rlkey=ozil85igh4w84tsdf6yecpnva

Updates: Participating centers: Yale, Tufts, Duke, Baylor, JHU, Houston Methodist

- 49 subjects entered as of 11/15/23

Interested? – Penn, Baptist Memorial Memphis, UCSF, Northwestern

Next step: Joey to reach out to the interested sites to clarify if they’ve completed IRB and/or DUA. Also recommend a data quality check and completeness survey.

Goal: To lock on data collection at end of December 2023; Statistician time to be allocated for Jan/Feb

- Liver biopsy study (Anju, Yas, Maryjane): Participating site PIs should follow the guidance in the “PI Instructions” Word doc, data collection form, DUA and protocol also included:

https://www.dropbox.com/scl/fo/aw9696ipg8ligs35jm422/h?dl=0&rlkey=34ny8mu5nwbdw62n2qhy0sn23

Status: Currently don’t have a central/coordinating IRB

Updates: Maryjane suggested excellent ideas for next steps, e.g. validating the liver risk score from CUMC

Next steps: Maryjane to reignite group and next steps in terms of protocol, sample size, CRF variables

Goal: Select site to host RedCAP and coordinate data entry

- Pre-advanced therapies renal function assessment and risk assessment (Mirnela):

Status: First draft completed, Mirnela reviewing

Next steps: Target journal TBD

- Preserving the kidney in HT recipients: from induction therapies to long term (Andriana, Mirnela, Varinder, Luise):

Nephrologist and PharmD also on the team. First drafts of sections have been submitted.

Status: Liaising with AST, have a list of writers and an outcome

Next steps: Making writing assignments, first draft

- State of the Art Review type paper on induction therapy in HT (Andriana, Johanna, Nadia):

Updates: Submitted in October for JACC:HF

Status: Pending reviewer comments

- HCV NAT treatment survey (Sonu and Roopa): Initial email was sent to the WiTMCS group and TX directors (12 responses total - target 45).

Status: A second prompt through the WiTMCS website

Next steps: Email through WiTMCS new membership groups

- “How To” paper on ambulating with tMCS (Anju): Pending publication of another paper. Anju to begin practical review from September’s meeting.

- COVID-19 donors and subsequent recipient CAV risk (Andriana): Looking for collaborators, esp from centers that do post-transplant IVUS assessments. Planning to start in the next few weeks.

- COVID-19 in HT recipients and subsequent rejection/CMV/CAV risk (Preethi): Pending updates

- Transplant recipients with a history of GCM (Luise): Pending updates

- Survey of women VAD/TX leaders (Varinder):

Status: Survey has been distributed, data collected.

Next steps: Download data from survey platform and begin analysis.

- Proposed cardiogenic shock Impella wean off VA-ECMO study, next step to apply for a grant for Abiomed (Copeland): Group forming, draft protocol circulating. Pending a follow-up meeting.

- ERAS VAD/TX study proposal (Copeland): Pending updates.

- Cardiac surgery research project (Larson): Pending updates. Sharon was planning to connect with other surgeons in the WITMCS group and collect ideas and then present options at our research group meeting (Hannah C, Amy H, Amy F, Marzia L etc)

- Thursday evening co-writing group 5-6.30 pm ET: All are welcome! https://wellforce-hipaa.zoom.us/j/5788493823?from=addon